## Cutover Plan
Concur Project Cutover, updated on 5 May 2026
BAYER EU DC - Portugal & Spain - Go Live Portugal only
Task # | Site | Product | Item | Start | End | Status | Person Responsible | Comment/Notes | Dependencies
PRE-PROD PREPARATION
1 | US DC BAYER | All | Communication to end users | 2026-05-05 | 2026-06-16 | In Progress |  | Employees needs to know when to complete last report, approve last reports, Credit Card transactions etc. | some training already completed in the week of 27 April. Processor/Admin traning - Concur to offer a BOT session end of May.
2 | EU DC BAYER | AppZen | Client ensures all requirements and timelines have been shared with AppZen | 2026-04-01 |  | Completed |  |  | Concur US will be connected to AppZen US, and simultaneously, Concur EU will be connected to AppZen EU. This arrangement ensures both instances can operate in parallel.
EXPENSE PRODUCTION BUILD
13 | EU DC BAYER | Expense | Copy configuration from Test to Production | 2026-05-26 | 2026-06-03 | Not Started | Concur Expense FC | Expense testing to be completed by 22 May
14 | EU DC BAYER | Travel | Concur verifies Employee Extract to Travel job success |  |  | Not Started | Concur TC
15 | EU DC BAYER | Integration | BAYER connects productive interfaces to the new Concur EU DC entity | 2026-06-03 |  | Not Started |  | all interfaces to be considered
LOADING PRODUCTION IMPORT FILES
21 | EU DC BAYER | Integration | Replicate cost object hierarchy, Load Lists and EE import files |  |  | Not Started |  |  | Company hierarchy is needed before Employee Load
22 | EU DC BAYER | Integration | Review load error report |  |  | Not Started
SYSTEM INTEGRATION
26 | EU DC BAYER | Travel | Concur verifies HMC Settings / Travel Integration - Employee Import Updates Name Fields - Synchronize Name Fields between Travel and Expense - Allow Pre-expense Airfare |  |  | Not Started | Concur Travel FC
27 | EU DC BAYER | Travel | Concur verifies Module Management settings - Allow Empty Travel Approval Hide - User-editable Name Fields - User-Editable Name Prefix - User-Editable Name Suffix - Travel Discounts By Org Unit - Profile Displays Org Unit - Job Title Required - Purge inactive profiles from GDS - Purge inactive profiles (days) |  |  | Not Started | Concur Travel FC
CONCUR PRODUCTION VALIDATION
29 | EU DC BAYER | Expense | Concur assigns the ASC permissions to applicable client project team members |  |  | Not Started | Concur Expense FC |  | Employee Upload needs to be completed first
Client VALIDATION
32 | EU DC BAYER | Travel | Client confirms Travel Info section has correct Travel related information |  |  | Not Started |  |  | Travel Policy Administrator permission
33 | EU DC BAYER | Expense | Cursory review of user interface. Review & validate employee forms & fields Review & validate report forms & fields Review & validate expense types, forms & fields Review & validate allocation forms | 2026-06-05 | 2026-06-10 | Not Started
END USER ROLLOUT
39 | EU DC BAYER | All | Go Live: send end user communications for new site note users will need to register for mobile app |  |  | Not Started
40 | EU DC BAYER | All | Go Live on Integrated Prod system | 2026-06-16 | 2026-06-30 | Not Started
41 | EU DC BAYER | All | Monitor system activity | 2026-06-16 | 2026-06-30 | Not Started | Concur TC

## Reference (hidden)
Responsible | Status
Sven Ohlsen | Not Started
Sonja Bloemer | Delayed
Vladimir Vrba | In Progress
Linda Jokuff | On Hold
Sebastian von Stein | Completed
Philipp Glawogger | N/A for this Project
Tufan Dede
Christopher Feuerecker