## Project Tasks
Task# | Complete% | Task Level | Task Name | Duration | Start | Finish | Predecessors | Successors | Constrain Type | Resources
1 | 64% | 1 | EMEA Wave 1: EXPENSE ES & PT | 264 | 2026-01-08 | 2026-09-28 |  |  | As Soon As Possible
2 | 100% | 2 | Getting Started Phase | 15 | 2026-01-08 | 2026-01-22 |  |  | As Soon As Possible
3 | 100% |  | Project Planning, Initiation, Assigning Resources | 13 | 2026-01-08 | 2026-01-20 |  | 4 | As Soon As Possible | person1
4 | 100% |  | Kickoff call | 3 | 2026-01-20 | 2026-01-22 | 3 | 7,42,11 | As Soon As Possible | person2
5 | 64% | 2 | Analysis & Design Phase | 237 | 2026-01-23 | 2026-09-16 |  |  | As Soon As Possible
6 | 99% | 3 | Design | 34 | 2026-01-29 | 2026-03-03 |  |  | As Soon As Possible
7 | 100% |  | Functional Design Session (Gap Analysis) via Teams | 8 | 2026-01-29 | 2026-02-05 | 4 | 9,8 | Start No Earlier Than | person3
8 | 100% |  | Expense Design agreed on | 26 | 2026-02-06 | 2026-03-03 | 7 | 21 | As Soon As Possible | person4
9 | 90% |  | Technical Design Call | 1 | 2026-02-06 | 2026-02-06 | 7 |  | Start No Earlier Than | person4
10 | 58% | 3 | Credit Card Feed Requests | 237 | 2026-01-23 | 2026-09-16 |  |  | As Soon As Possible
11 | 100% |  | Client submits completed cc matrix to Concur | 62 | 2026-01-23 | 2026-03-25 | 4 | 12 | As Soon As Possible | person5,person4
12 | 100% |  | Concur creates PR requests for each cc feed requested | 30 | 2026-03-26 | 2026-04-24 | 11 | 13 | As Soon As Possible | person5,person5
13 | 100% |  | Forms sent to Client | 2 | 2026-04-27 | 2026-04-28 | 12 | 14 | As Soon As Possible | person5,person6
14 | 100% |  | Client remits completed forms | 10 | 2026-04-29 | 2026-05-08 | 13 | 15 | As Soon As Possible | person5
15 | 100% |  | Formal notice sent from Concur CCE-Operator to card providers | 2 | 2026-05-11 | 2026-05-12 | 14 | 16 | As Soon As Possible | person5
16 | 100% |  | Bank provides filenames | 24 | 2026-05-13 | 2026-06-05 | 15 | 17 | As Soon As Possible | person5
17 | 0% |  | Concur sets up filemovers and feeds | 82 | 2026-06-08 | 2026-08-28 | 16 | 18 | As Soon As Possible | person5
18 | 0% |  | CC feeds loaded into Prod system | 7 | 2026-09-10 | 2026-09-16 | 17 |  | Start No Earlier Than | person5
19 | 81% | 2 | Configuration & Validation Phase | 98 | 2026-03-04 | 2026-06-09 |  |  | As Soon As Possible
20 | 100% | 3 | Configuration | 22 | 2026-03-04 | 2026-03-25 |  |  | As Soon As Possible
21 | 100% |  | Migration and Configuration of country-specific requirements to Test | 21 | 2026-03-04 | 2026-03-24 | 8 | 22 | Start No Earlier Than | person4,person3
22 | 100% |  | Site Walkthrough Prep and Integral Run Through | 1 | 2026-03-24 | 2026-03-24 | 21 | 23 | As Soon As Possible | person4
23 | 100% |  | Site Walkthrough | 1 | 2026-03-25 | 2026-03-25 | 22 | 24 | As Soon As Possible | person4
24 | 100% |  | Handover of the system to Client | 1 | 2026-03-25 | 2026-03-25 | 23 | 26 | As Soon As Possible | person4
25 | 75% | 3 | Client Testing Phases | 76 | 2026-03-26 | 2026-06-09 |  |  | As Soon As Possible
26 | 100% |  | Test Phase I - User Interface | 16 | 2026-03-26 | 2026-04-10 | 24 | 27 | As Soon As Possible | person3
27 | 93% |  | Test Phase II - Functional | 40 | 2026-04-13 | 2026-05-22 | 26 | 28 | As Soon As Possible | person3
28 | 0% |  | ICS connection established | 7 | 2026-05-26 | 2026-06-01 | 27 | 29 | As Soon As Possible | person3
29 | 0% |  | Test Phase III - Interface Testing & End to End Testing | 8 | 2026-06-02 | 2026-06-09 | 28 | 30 | As Soon As Possible | person3
30 | 0% |  | Client provides feedback on if all testing is completed | 1 | 2026-06-09 | 2026-06-09 | 29 | 31,34,33 | As Soon As Possible | person3